## Action Items
Project Dashboard
| Project Name: | NPD Template Tasks list for overall project
| Project Manager: | TBD - Project Manager
| Exported: | 2026-04-03 21:38:07
Reference ID# | Description of Action Item | Source of Action Item | Assigned to | Date Entered | Status | Due Date | Date Closed | Final Result/Outcome
1 | Failure History | Gate 2 |  | 2025-01-04 | Planned
2 | Human Centered Design Plan | Gate 2 |  | 2025-01-04 | Planned
3 | Customer Requirements Document (CRD) | Gate 2 |  | 2025-01-04 | Planned
4 | Technical Feasibility Analysis | Gate 2 |  | 2025-01-04 | Planned
5 | Technical Risk Analysis | Gate 2 |  | 2025-01-04 | Planned
6 | Direct Material Cost Estimates | Gate 2 |  | 2025-01-04 | Planned
7 | Manufacturing Feasibility Analysis | Gate 2 |  | 2025-01-04 | Planned
8 | Operational Cost Estimates | Gate 2 |  | 2025-01-04 | Planned
9 | Project Plan | Gate 3 |  | 2025-01-04 | Planned
10 | Project Risk Register | Gate 3 |  | 2025-01-04 | Planned
11 | Project Schedule | Gate 3 |  | 2025-01-04 | Planned
12 | Peer Safety Review | Gate 3 |  | 2025-01-04 | Planned
13 | Preliminary Design Review | Gate 3 |  | 2025-04-02 | Planned
14 | Human Centered Design Review | Gate 3 |  | 2025-04-20 | Planned
15 | System Requirements Document (SRD) | Gate 3 |  | 2025-06-16 | Planned
16 | System Architecture Document (SAD) | Gate 3 |  | 2025-06-16 | Planned
17 | Detailed Product Design Requirements | Gate 3 |  | 2025-06-16 | Planned
18 | Preliminary BOM | Gate 3 |  | 2025-06-22 | Planned
19 | Test Plan | Gate 3 |  | 2025-07-10 | Planned
20 | Design Strategy Review with Supply Chain | Gate 3 |  | 2025-10-01 | Planned
21 | Product Security Plan (PSP) | Gate 3 |  | 2025-11-01 | Planned
22 | Threat Model and Product Security Risk Assessment | Gate 3 |  | 2025-12-03 | Planned
23 | Product Approvals Strategy | Gate 3 |  | 2025-12-03 | Planned
24 | Model Structure Master Drawing | Gate 3 |  | 2025-12-03 | Planned
25 | Lifecycle Service Org Alignment | Gate 3 |  | 2025-12-03 | Planned
26 | Marketing and Digital Debrief | Gate 3 |  | 2025-12-03 | Planned
27 | Customer Care Checklist | Gate 3 |  | 2025-12-03 | Planned
28 | Environmental, Health, and Safety (EHS) Review | Gate 3 |  | 2025-12-03 | Planned
29 | Product Environmental Compliance Review (Initial) | Gate 3 |  | 2025-12-03 | Planned
30 | Business Systems Scope Sheet | Gate 3 |  | 2025-12-03 | Planned
31 | Trade Compliance Assessments | Gate 3 |  | 2025-12-03 | Planned
32 | Supplier Selection and Quoting | Gate 3 |  | 2025-12-03 | Planned
33 | Strategic Sourcing Review | Gate 3 |  | 2025-12-03 | Planned
34 | Site Inventory Checkbook Entry | Gate 3 |  | 2025-12-03 | Planned
35 | Global Manufacturing & Distribution Plan | Gate 3 |  | 2025-12-04 | Planned
36 | Legacy Product Discontinuance/Transition Strategy and Plan | Gate 3 |  | 2026-01-01 | Planned
37 | Projected Inventory & Equipment Cost Liability Analysis | Gate 3 |  | 2026-01-15 | Planned
38 | Unique Parts Analysis (Preliminary) | Gate 3 |  | 2026-01-31 | Planned
39 | Customer Impact Analysis for legacy products | Gate 3 |  | 2026-02-01 | Planned
40 | Peer Safety Review | Gate 4 |  | 2026-02-16 | Planned
41 | Final Design Review | Gate 4 |  | 2026-02-20 | Planned
42 | Sales & Operations Plan (S&OP) | Gate 4 |  | 2026-07-01 | Planned
43 | Business System Readiness Review | Gate 4 |  | 2026-07-01 | Planned
44 | Product Service Plan | Gate 4 |  | 2026-07-21 | Planned
45 | Certification Templates and Applications | Gate 4 |  | 2026-08-10 | Planned
46 | Configuration Data Sheet (CDS) | Gate 4 |  | 2027-01-01 | Planned
47 | User Interface Requirements Document (UIRD) | Gate 4 |  | 2027-01-10 | Planned
48 | Price List | Gate 4 |  | 2027-01-10 | Planned
49 | Model Forecast & Options Mix | Gate 4 |  | 2027-01-10 | Planned
50 | Field Trial Plan / Results | Gate 4 |  | 2027-01-15 | Planned
51 | Product Message Strategy | Gate 4 |  | 2027-02-01 | Planned
52 | Quoting Plan | Gate 4 |  | 2027-03-01 | Planned
53 | Education Training Plan | Gate 4 |  | 2027-03-09 | Planned
54 | Specification Control Drawing (SCD) | Gate 4 |  | 2027-03-10 | Planned
55 | Peer Reviews | Gate 4 |  | 2027-03-20 | Planned
56 | FMEDA Report | Gate 4 |  | 2027-05-30 | Planned
57 | Test Results | Gate 4 |  | 2027-06-25 | Planned
58 | Final BOM | Gate 4 |  | 2027-08-01 | Planned
59 | User Testing and Evaluation | Gate 4 |  | 2027-11-01 | Planned
60 | Troubleshooting Guide | Gate 4 |  | 2027-11-09 | Planned
61 | Configurator Product Requirements | Gate 4 |  | 2027-11-10 | Planned
62 | Intellectual Property Assessment | Gate 4 |  | 2028-01-10 | Planned
63 | Declaring Import Assists | Gate 4 |  | 2028-01-10 | Planned
64 | Threat Model and Product Security Risk Assessment | Gate 4 |  | 2028-02-02 | Planned
65 | Product Approvals Agency Applications | Gate 4 |  | 2028-03-25 | Planned
66 | Environmental, Health, and Safety (EHS) Review | Gate 4 |  | 2025-12-01 | Planned
67 | Product Environmental Compliance Review (Updated) | Gate 4 |  | 2026-01-15 | Planned
68 | Business Sizing and configuration test plans | Gate 4 |  | 2026-02-16 | Planned
69 | Product Advisor/Configurator/GMS Release Schedules | Gate 4 |  | 2026-02-20 | Planned
70 | Supplier Assessment (ESAC) & Recommendations | Gate 4 |  | 2026-07-01 | Planned
71 | Supplier DFM/DFT Reviews & Recommendations | Gate 4 |  | 2026-05-20 | Planned
72 | Part/Assembly Drawing Reviews | Gate 4 |  | 2026-05-20 | Planned
73 | Tooling Purchase Orders | Gate 4 |  | 2026-06-01 | Planned
74 | Inspection Plans & Equipment | Gate 4 |  | 2026-07-10 | Planned
75 | Product Packaging | Gate 4 |  | 2026-03-31 | Planned
76 | Logistics Requirements | Gate 4 |  | 2026-12-01 | Planned
77 | Declaring Import Assists | Gate 4 |  | 2027-02-01 | Planned
78 | Set Up and Verify Purchasing Parameters | Gate 4 |  | 2027-03-20 | Planned
79 | Materials Readiness Review | Gate 4 |  | 2027-03-30 | Planned
80 | Site Inventory Checkbook Entry | Gate 4 |  | 2026-03-18 | Planned
81 | Trade Compliance Review and System Setup | Gate 4 |  | 2026-03-18 | Planned
82 | Manufacturing Risk Analysis | Gate 4 |  | 2026-06-15 | Planned
83 | Equipment Safety Review and Job Hazard Assessment | Gate 4 |  | 2026-04-01 | Planned
84 | Declared Import Assists for Operations Equipment | Gate 4 |  | 2026-04-09 | Planned
85 | Manufacturing Software Requirements Specification | Gate 4 |  | 2026-04-09 | Planned
86 | Manufacturing Process Documentation | Gate 4 |  | 2026-04-09 | Planned
87 | Manufacturing Process Qualification (MPQ) & Test Station Validation Plan | Gate 4 |  | 2026-04-09 | Planned
88 | Manufacturing Verification Test Plan (MVT) | Gate 4 |  | 2026-04-09 | Planned
89 | Manufacturing Readiness Review (MRR) | Gate 4 |  | 2026-04-09 | Planned
90 | New Service Center Part/Model Numbers | Gate 4 |  | 2026-04-09 | Planned
91 | List of Service Sites to Support the New Product | Gate 4 |  | 2026-04-09 | Planned
92 | Product Management Discontinuance Plan | Gate 4 |  | 2026-04-09 | Planned
93 | Unique Parts Analysis (Final) | Gate 4 |  | 2026-04-09 | Planned
94 | Material Liability Analysis | Gate 4 |  | 2026-04-09 | Planned
95 | Supplier Communication Strategy | Gate 4 |  | 2026-04-09 | Planned
96 | Critical Action Items Closed | Gate 5 |  | 2026-04-09 | Planned
97 | Failure Analysis Plan | Gate 5 |  | 2026-04-09 | Planned
98 | Product Audit Test Plan | Gate 5 |  | 2026-04-09 | Planned
99 | Business Systems Ready and Deployed | Gate 5 |  | 2026-04-09 | Planned
100 | Manufacturing Verification and Supply Chain Readiness Review | Gate 5 |  | 2026-04-09 | Planned
101 | Booking Release | Gate 5 |  | 2026-04-09 | Planned
102 | Product Quality Certificates | Gate 5 |  | 2026-04-09 | Planned
103 | Launch Materials | Gate 5 |  | 2026-04-09 | Planned
104 | Knowledge Management Entry/Entries | Gate 5 |  | 2026-04-09 | Planned
105 | Sales, Service and Customer Care Training Content | Gate 5 |  | 2026-04-09 | Planned
106 | Service Plan | Gate 5 |  | 2026-04-09 | Planned
107 | Device Description | Gate 5 |  | 2026-04-09 | Planned
108 | User Interface DVT Results | Gate 5 |  | 2026-04-09 | Planned
109 | Theory of Operations | Gate 5 |  | 2026-04-09 | Planned
110 | Product Security Test Plan (PSTP) | Gate 5 |  | 2026-04-09 | Planned
111 | SBOM and Vulnerability Monitoring (SBOM) | Gate 5 |  | 2026-04-09 | Planned
112 | Security Guidelines for User Documentation | Gate 5 |  | 2026-04-09 | Planned
113 | Product Approvals Certificates | Gate 5 |  | 2026-04-09 | Planned
114 | Declaration of Conformity Document | Gate 5 |  | 2026-04-09 | Planned
115 | Environmental, Health, and Safety (EHS) Review | Gate 5 |  | 2026-04-09 | Planned
116 | Product Environmental Compliance Review (Final) | Gate 5 |  | 2026-04-09 | Planned
117 | Part Supplier Ramp-Up & Phase-Out Plan | Gate 5 |  | 2026-04-09 | Planned
118 | PPAP Documentation & Results | Gate 5 |  | 2026-04-09 | Planned
119 | Supplier Contracts | Gate 5 |  | 2026-04-09 | Planned
120 | Purchasing Transitioned to Production Buyers | Gate 5 |  | 2026-04-09 | Planned
121 | Intraco Prospectus | Gate 5 |  | 2026-04-09 | Planned
122 | Process & Parts Obsolescence Plan | Gate 5 |  | 2026-04-09 | Planned
123 | MVT Results | Gate 5 |  | 2026-04-09 | Planned
124 | Service Catalog | Gate 5 |  | 2026-04-09 | Planned
125 | QSR Operational Readiness | Gate 5 |  | 2026-04-09 | Planned
126 | Reserves for Supplier Committed Material | Gate 5 |  | 2026-04-09 | Planned
127 | Reserves for Global On-Hand Inventory | Gate 5 |  | 2026-04-09 | Planned